## Slide 1: Roadmap for Improving
Small & Minority-, Women- and Veteran- Owned Business Participation in State Contracting
September 14, 2017
Chris Liu, Director
Department of Enterprise Services
Presenter:
Rex Brown, Administrative Director
Business Diversity Subcabinet
Department of Enterprise Services

## Slide 2: Contact Info:
Chris Liu, Director
Department of Enterprise Services
Desk: 360.407.9201
Cell: 360.628.0058
Chris.Liu@des.wa.gov
Rex Brown, Administrative Director
Business Diversity Subcabinet
Department of Enterprise Services
Desk: 360.407.7926
Cell: 360.763.2744
Rex.Brown@des.wa.gov

## Slide 3: Achieving What the Public Wants Through Technical Teams
The most important thing the Subcabinet is interested in is outcomes for our customers.

## Slide 4: How Technical Teams Operate
  Facilitation of work sessions of selected representative subject matter experts and consensus-driven decision making
Notes:   to:
    Craft a common definition of business and functional requirements to be included in OMWBE reporting or tracking through an alternative system
    A definition of scope and high-level design for the Business Diversity Interface
    Development of the plan for detailed design and system implementation.

## Slide 5: Our Technical Teams
Measurement
Framework
Improved
Certification
Technical Assistance
Diversity Culture &
Framework
Community of
Practice (CoP)
Engagement and
Assistance CoP
AGO Opinion Disparity Study
Legal Framework on a Parallel Path

## Slide 6
Detailed Action Plan:
Task | Task Lead | Partners | Expected Outcome | Status | Due Date
Measurement Framework | OMWBE, LNI | DSHS, DOC, DES | Create suite of measures to provide the best dashboard for accountability and improving results. Increase use and reliability of data. | Ongoing | 8/31/17 (Phase II) 9/28/18 (Phase III)
Improved OMWBE Certification | OMWBE |  | Eliminate any unnecessary barriers and improve certification timeframes. | Ongoing | 10/01/17 (Phase II) 9/28/18 (Phase III)
Community of Practice (CoP) | DSHS, WSDOT, DES, OMWBE | HCA | Embed a broad understanding of equity, diversity and inclusion throughout community of procurement professionals. | Ongoing | 8/31/17 (Phase II) 9/28/18 (Phase III)
Technical Assistance | OMWBE, DES | ORIA, Commerce | Create a system for small business to customize their needs to available resources. Central web site with “triage” services. Feedback loop for quality control. | Ongoing | 10/01/17 (Phase II) 9/28/18 (Phase III)
Disparity Study | DES | 33 State Agencies | Provide necessary data needed to understand whether minority-, women- and veteran-owned businesses have equal access to contracting opportunities. | Ongoing | 1/31/19
Goal 2 Prosperous Economy Quality of Life 4.1.a Increase state agency and educational institution utilization of state-certified small businesses
Notes: Certification:
Change Phase II date to 10/1/17
This will reflect when we go live for online applications.
Thanks!

## Slide 7: Measurement Framework
The Three Areas of Measurement:
  Accountability: Telling the Full Story
  Improving Data Quality and Confirming Data
  Improving Data Completeness

## Slide 8: Measurement Framework Team 1: Accountability- Telling The Full Story
Sponsors: OMWBE, DES, LNI, WSDOT
Vision for the future:
What does success look like?
  Meaningful measures really matter. They help drive how and where we improve.
  Best dashboard to drive meaningful results?

## Slide 9
Confirm business rules for the diversity spend report
Measurement Framework Team 2:
Improving Data Quality and Confirming Data
Sponsors: DES, HCA, LNI, DSHS

## Slide 10: Measurement Framework: Data Completeness
Measuring certified business participation in:
identified spend areas
on a regular real-time basis
Sponsors: DES, WSDOT

## Slide 11: Technical Team for Technical Assistance
Provide to small businesses:
Direct assistance
Options for enhancing resource referral services

## Slide 12: Technical Team to Improve of OMWBE Certification
Working to eliminate any unnecessary barriers and improve certification time frames.

## Slide 13: Technical Team for Diversity Culture and Framework
Embed a broad understanding of:
Equity
Diversity and
Inclusion
throughout the State procurement professionals of WA

## Slide 14: Technical Team for Engagement and Assistance Framework
Develop relationships with Small, Veteran, Minority, Women, Minority-Women owned businesses by:
Collecting customer experience data
Engaging vendors
Removing barriers

## Slide 15: Questions and Answers
Thank You!