## Slide 1: Skyline Hospital Modernization Project
Presentation for PRC Approval GCCM Project Delivery
September 26, 2019

## Slide 3: Agenda – Dick
Introductions - Dick
Skyline Hospital - Robb
Project Team - Dick
Purpose of GCCM Application - Dick
Project Description - John
Benefits of GCCM Project Deliver – Dick
Schedule - Dick
Summary/Questions - Robb

## Slide 4: Skyline Hospital-Robb
  Originally constructed in 1952 through the Hill-Burton Act, with the addition of one wing in the early 1970’s. A second $2.7 million renovation in 1998 enhanced the facility with a surgery suite, an emergency room, physical therapy building, laboratory and admitting area. A year later, the hospital purchased an adjoining seven-acre parcel of land to facilitate long-range plans
  2010 $15M Patient Bed Wing GCCM Process
  More recently, Skyline has added specialty services to better serve the community. These include:
    General Surgery
    Infusion Services
    Podiatry
  Current Status is a Critical Access Hospital
  Importance Of Modernization Project
  Goals and Expectations

## Slide 5: Project Team -Dick
  Skyline Hospital-Robb Kimmes CEO
    Overall Responsibility
  DBPMLLC-Dick Bratton PM/Owner Rep
    Project Management
    Onset to Completion
    Ongoing GCCM Experience w/SPMC /LCCHC/Samaritan/KVH
  Blue Room-John McLean AOR
    Variety of GCCM Project Experience
    Considerable Healthcare Experience
    GCCM Credible A/E Team Composition
  Foster Pepper - Counsel
    Contract Experience with RCW 39.10
    AIA A133/201 and AIA B133 in draft form

## Slide 6: Purpose of GCCM Application-Dick
Skyline Hospital Project Importance
  Project Meets GCCM Criteria
    Critical Scheduling, Phasing, Transition
    Early GCCM Interaction Required for Successful Project
    3 step selection process
  Schedule and Operational Management
    Keep all functions operational during construction
  Cost Advice
  Rural Remote Location
  Early Team Interaction for Scope Evaluations/Options
  Benefit to Community
  Skyline Hospital Team Fully Prepared

## Slide 7: Project Description-John

## Slide 13: Benefits of GCCM Project Delivery-Dick
Owner/Designer/Contractor Collaboration
  Utilize Team Expertise Early at DD
Compliant to RCW 39.10 Policies & Procedures
Review of Hospital Operations Challenges
Establish Budget/Provide DD with Budget Advice
Identify and Coordinate Long Lead Items
Full CD Set Detailed with GCCM Input
MACC at 90% CD, VE and Budget Reconciliation
Interactive Design/Contractor/PM Team Group Effort for BIM Modeling and Clash Mitigation
GCCM Influence and Coordination of Move Transition

## Slide 14: Schedule-Dick
GC/CM PCARB Application Submittal August 20, 2019
SH PRC Presentation September 26, 2019
GC/CM Delivery Approval October 7, 2019
Official State Authority Notice October 2019
GC/CM RFQ Due November 2019
GC/CM Interviews November 2019
GC/CM RFFP-Selection November 2019
DD Design Complete / Baseline Estimate January 2020
Baseline MACC 90% Construct Docs February 2020
Construction Docs 100% March 2020
Permitting March 2020
Final MACC March 2020
Site Mobilization April 2020
Construction Completion May 2021

## Slide 15: Summary-Robb
Applicant Final Comments
Questions