## All Projects Summary
State LEED Projects
Master List
GA | Project Information |  | Project | Construction | Project | Project | Submittal Received | [6 empty] | LEED | Energy
Green | Project | Project Name | No. | Cost | Square | Manager | (Note: Dates not shaded are anticipated submittal dates.) | [6 empty] | Certification | Data Needed | Design | Construction | Occupied
Bldg # | Mgt. |  |  | Estimate | Footage |  | Exemption | Pre-Design | Schem. D. | Design Dev. | Const.Doc. | Subst. Compl. |  | Awarded
G 05-006 | DES-A | Military - Washington Youth Academy | 07-189 | 5000000 | 20000 | Yelena Semenova |  | LEED Silver |  |  |  | 2009-01-07 |  | 2010-08-01
G 08-002 | DES-A | Centralia College-Science Complex | 03-218 | 20400000 | 70000 | Jim Copland |  | LEED Gold |  |  |  | 2009-03-09 |  | 2010-08-01
G 08-008 | DES-A | Clark College - East County Satelite Campus | 05-099 | 20470000 | 70000 | Todd Flynn |  | LEED Gold |  |  |  | 2009-04-22 | [5 empty] | 1
G 08-041 | DES-A | Clover Park TC - Allied Heath Care Facility | 06-092 | 21480000 | 56000 | Erasmus Othieno |  | 2006-06-16 | 2008-03-19 | 2008-05-01 | 2008-09-01 | 2010-12-01 |  | ? |  | 1
G 08-012 | DES-A | Grays Harbor CC - Voc. Ed. Renovation | 05-186 |  |  | Stacy Simpson | 2006-02-06
G 05-010 | DES-A | Grays Harbor CC - Childcare Center | 09-015 | 1635000 | 6246 | Stacy Simpson |  | LEED Gold |  |  |  | 2010-02-04 |  | 2010-09-14 |  |  |  | 1
G 09-002 | DES-A | Olympic College - Humanities Building | 05-187 | 21200000 | 85012 | Ronnie Hill |  | LEED Gold |  |  |  | 2010-01-08 |  | 2011-08-01 |  |  |  | 1
G 07-005 | DES-A | Olympic College - Sophia Bremer Child Development Ctr | 08-256 | 3318000 | 12890 | Ronnie Hill |  | 2008-12-01 | 2009-02-01 | 2009-04-01 | 2009-10-01 | 2010-10-01 |  |  |  |  | 1
G 05-012 | DES-A | Peninsula College - Business & Humanities Center | 06-125 | 26000000 | 63000 | Jim Copland |  | 2009-06-11 | 2009-06-11 | 2009-06-11 | 2009-02-09 | 2011-03-28 |  | ? |  |  | 1
G 05-015 | DES-A | Pierce College - Ft. Steilacoom - Science & Tech Center | 03-200 | 21300000 | 70000 | Todd Flynn |  | LEED Gold |  |  |  | 2010-02-25 |  | 2010-08-04 |  |  |  | 1
G 05-016 | DES-A | Pierce College - Puy - Communication, Arts & Allied Health | 03-198 | 19000000 | 60000 | Todd Flynn |  | LEED Gold |  |  |  | 2010-09-22 |  | 2011-02-18 |  |  |  | 1
G 08-007 | DES-A | SPSCC - Science Complex | 03-223 | 18546500 | 66990 | Bala Ramaya |  | LEED Gold |  |  |  | 2008-10-30 |  | 2010-05-01
G 05-022 | DES-A | SPSCC-Vocational Tech Building | 08-150 | 8550000 | 40000 | Bala Ramaya |  | LEED Gold |  |  |  | 2010-06-01 |  | 2011-04-11 |  |  |  | 1
G 08-007 | DES-A | SPSCC-Instructional Building 23 | 08-150 | 16831000 | 30000 | Bala Ramaya |  | LEED Gold |  |  |  | 2010-09-01 | [5 empty] | 1
G 08-033 | DES-A | SPSCC-Building 22 Renovation | 08-150 | 23700000 | 89000 | Yelena Semenova |  | 2009-10-23 | 2009-12-31 | 2010-04-30 | 2010-09-30 | 2013-01-02 |  |  |  | 1
G 08-013 | DES-A | Tacoma CC-Early Childhood Edu. & Child Care Center | 06-205 | 4242000 | 15000 | Yelena Semenova |  | LEED Gold |  |  |  | 2008-07-18 |  | Oct 09
G 05-026 | DES-A | Tacoma CC-Health Careers Center | 07-142 | 29935000 | 69266 | Yelena Semenova |  | 2009-10-01 | 2010-03-01 | 2010-10-01 | 2011-07-01 | 2013-01-01 |  |  |  | 1
G 05-076 | DES-A | WA School for the Deaf, New Voc. Ed. & Support Bldg | 07-214 | 10900000 | 23134 | Dwayne Harkness |  | LEED Gold |  |  |  | 2009-08-01 |  | 2010-08-01
G 05-077 | DES-A | WA School for the Blind, New Phys. Ed. Center | 08-040 | 8000000 |  | Dwayne Harkness |  | LEED Silver |  |  |  | 2009-03-01 |  | Sept-09 |  |  |  | 1
G 08-035 | DES-A | Capitol Campus - O'Brien Bldg. | 07-022 | 27000000 | 103987 | Marziah Kiehn |  |  |  |  | 2009-05-27 | 2012-10-12 |  |  |  |  | 1
| DES-A | Lower Columbia College - Myklebust Gym Renovation | 12-001 | New Project |  | Ronnie Hill
G 08-005 | DES-B | Bellevue College - Science & Tech Bldg | 06-123 | 27500000 | 69511 | Bob Colasurdo |  | LEED Gold |  |  |  | 2008-11-01 |  | 2010-07-01
G 05-034 | DES-B | Bellevue College Health Sciences Building | 08-036 | 25538000 | 70000 | Bob Colasurdo |  | 2008-07-01 | 2010-02-15 | 2010-06-01 | 2010-11-15 | 2013-04-01 |  |  |  | 1
G 05-035 | DES-B | Bellingham TC - Campus Center | 08-070 | 22400000 | 74000 | Greg Rohner |  | 2008-03-05 | 2008-03-05 | 2008-07-02 | 2009-12-28 | 2012-03-01 |  |  |  |  | 1
G 05-036 | DES-B | Cascadia CC - Center for the Arts, Tech, & Global Interact | 06-144 | 26440529 | 54300 | Bob Kacel |  | 2006-09-15 |  | 2006-11-28 | 2007-12-05 | 2009-04-01 | [5 empty] | 1
G 05-038 | DES-B | Columbia Basin C - Social Science Ctr - Visual Arts Bldg. | 07-153 | 12410000 | 40520 | Dave Combs |  | 2008-07-01 | 2008-07-01 | 2008-12-01 | 2010-06-01 | 2012-09-01 |  |  |  | 1
G 05-001 | DES-B | Columbia Basin C - Business Education | 07-151 | 4715245 | 24000 | Dave Combs |  | LEED Gold |  |  |  | 2009-06-30 |  | 2010-07-01
G 09-003 | DES-B | Columbia Basin C - V Building Career & Tech Education Ctr | 07-152 | 1802000 |  | Dave Combs |  | 2/30/2008 | 2008-04-30 | 2008-07-31 | 2009-04-30 | [5 empty] | 1
G 09-004 | DES-B | Edmonds CC - Meadowdale Hall Renovation | 08-058 | 5534000 | 36100 | Linda Colasurdo |  | 2007-08-20 | 2007-08-20 | 2008-04-21 | 2008-11-10 | 2010-11-01 |  |  |  |  | 1
G 08-006 | DES-B | Everett CC - Undergraduate Education Center | 05-219 | 21000000 | 86000 | Joe Sullivan |  | LEED Silver |  |  |  | 2007-11-05 |  | Sept-09
G 05-040 | DES-B | Everett CC - Student Fitness & Health Center | 08-199 | 17000000 | 50000 | Jonathan Martin |  | LEED Gold |  |  |  | 2010-12-14 |  | 2012-06-22 |  |  | 1
G 05-041 | DES-B | Everett CC - Index Hall Replacement | 09-207 | 27000000 | 70000 | Linda Colasurdo |  | 2010-08-16 | 2010-08-16 | 2010-11-01 | 2011-05-01 | 2013-04-01 |  |  |  | 1
G 05-043 | DES-B | Green River CC - Salish Hall | 07-193 | 26281180 | 79996 | Julie Nakahara |  | LEED Silver |  |  |  | 2011-03-05 |  | 2012-06-01 |  |  | 1
G 05-044 | DES-B | Lake WA Tech - Allied Health Bldg. | 06-073 | 22669877 | 83500 | Bob Kacel |  | LEED Silver |  |  |  | 2011-05-02 |  | 2012-08-01 |  |  | 1
| DES-B | North Seattle CC - Intergrated Services Center | 06-132 | 12985473 | 47500 | Bob Kacel |  | LEED Gold |  |  |  | 2011-03-25 |  | 2010-10-01 |  | 1
G 07-001 | DES-B | North Seattle CC - Technology Building Renewal | 08-177 | 16000000 | 50600 | Bob Kacel |  | 2010-08-16 | 2010-08-16 | 2010-11-01 | 2011-10-01 | 2013-05-01 |  |  |  | 1
| DES-B | South Seattle CC - Colin Building Expansion | 10-063 | 3600000 | 10000 | Jonathan Martin |  |  | 2010-03-29 | 2010-06-14 | 2010-08-31 | 2011-03-01
G 08-019 | DES-B | Seattle Central CC - Wood Construction Center | 08-063 | 19600000 | 57229 | Lee Knawa |  | 2008-01-01 | 2008-01-01 | 2009-06-06 | 2009-01-01 | 2011-10-01 |  |  |  |  | 1
G 07-005 | DES-B | Skagit Valley CC - Science Bldg. | 05-200 | 21157000 | 65900 | Bob Colasurdo |  | LEED Platinum |  |  |  | 2008-11-01 |  | 2010-08-01
G 07-006 | DES-B | Skagit Valley CC - Academic & Student Support Building | 07-236 | 25433000 | 64230 | Bob Colasurdo |  | 2009-09-01 | 2009-09-01 | 2010-02-01 | 2010-06-01 | 2011-10-01 |  |  |  |  | 1
G 09-004 | DES-B | Spokane CC - Tech Ed Building | 07-132 | 19804000 | 70000 | Eric Benson |  | 2008-04-01 | 2008-04-01 | 2008-06-15 | 2009-11-24 | 2011-03-06 |  |  |  |  | 1
G 05-045 | DES-B | Spokane CC - Buiding 7 | 07-133 | 6405000 | 31571 | Eric Benson |  | 2007-12-26 | 2008-05-07 | 2009-03-18 | 2009-05-13 | 2010-11-10 |  |  |  |  | 1
G 05-046 | DES-B | Spokane Falls CC - Music Building | 07-134 | 9607000 | 47571 | Eric Benson |  | 2008-05-08 | 2008-05-08 | 2008-06-10 | 2009-07-01 | 2011-01-22 |  |  |  |  | 1
G 05-079 | DES-B | Spokane Falls CC - Classroom Bldg. | 07-148 | 12825910 | 51143 | Eric Benson |  | 2006-12-12 | 2007-09-01 | 2008-04-13 | 2009-11-01 | 2012-12-30 |  |  |  |  | 1
G 08-023 | DES-B | Spokane Falls CC - Business and Social Science | 04-192 | 14347980 | 70533 | Eric Benson |  | LEED Gold |  |  |  | 2008-08-01 |  | 2008-12-01
G 05-080 | DES-B | Spokane Falls CC - Early Learning Center | 07-149 | 2960000 | 16000 | Eric Benson |  | 2006-12-01 | 2007-09-01 | 2008-01-27 | 2008-05-27 | 2012-12-30 |  |  |  |  | 1
G 05-047 | DES-B | Spokane Falls CC - Science Building | 07-150 | 19547000 | 69825 | Eric Benson |  | 2008-02-15 | 2008-06-30 | 2009-01-30 | 2009-05-30 | 2011-02-25 |  |  |  |  | 1
G 05-047 | DES-B | Walla Walla CC - Clarkston Health Sciences | 05-162 | 2252000 |  | Dave Combs | 2006-10-12 | 2004-11-30 | 2005-08-12 | 2005-12-20 | 2006-05-15
G 05-047 | DES-B | Walla Walla CC - Center for Water and Environ. Studies | 05-210 | 2000000 | 10500 | Dave Combs |  | 2004-11-30 | 2005-09-27 | 2006-01-15 | 2006-04-10 | [6 empty] | 1
G 05-048 | DES-B | WSP - FTA Dormatory | 07-203 | 1900000 | 9484 | Jonthan Martin | 2008-09-02
G 05-049 | DES-B | Yakima Valley CC - Grandview Library | 09-172 | 3116878 | 12553 | David Lohrengel |  | 2009-09-01 | 2009-12-07 | 2009-03-01 | 2010-08-09 | 2011-06-30 |  |  |  |  | 1
G 05-050 | DES-B | Yakima Valley CC - Brown Dental Renovation | 07-155 | 3898000 |  | David Lohrengel | 2008-05-19 | 2007-11-21 | 2007-11-21 | 2008-01-02 | 2008-04-02 | 2009-07-01
G 05-052 | DOC | Coyote Ridge Corrections Center | 06-313 | 190000000 | 564000 | Jack Olson |  | LEED Gold |  |  |  | 11/31/08 | Oct-09 | 2010-06-01
G 07-002 | DOC | WSP - South Close - Voc Ed Building | 06-314 | 8351351 | 22400 | Nanette Graham | On Hold | 2007-07-09 | 2007-07-18 | 2007-12-05 | 2008-04-10 | 2010-06-29 |  |  |  |  | 1
G 07-003 | DOC | WSP - South Close - Warehouse | 06-314 | 5280384 | 21600 | Nanette Graham |  | LEED Silver |  |  |  | 2010-06-29 |  |  |  |  | 1
G 07-008 | DOC | CCCC - 100 Bed Expansion | 06-330 | 4878336 | 16300 | Ed Hampton |  | LEED Silver |  |  |  | 2009-07-06
G 08-025 | DOC | WSP - South Close - Health Unit | 06-314 | 22931500 | 49022 | Nanette Graham |  | LEED Silver |  |  |  | 2010-06-29 | [5 empty] | 1
G 05-053 | DOC | MCC - Hazardous Waste/Vehicle storage | 06-305 | 1403990 | 6000 | Tom Davis | On Hold | 2006-06-08 | 2009-10-23 | 2010-02-05 | 2010-07-30 | 2012-06-01 |  |  |  | 1
G 08-020 | DOC | MCC - Warehouse Facility | 06-305 | 5985000 | 26000 | Tom Davis | On Hold | 2006-06-08 | 2009-10-23 | 2010-02-05 | 2010-07-30 | 2012-06-01
G 05-054 | DOC | MCC - Health Care Facility | 06-305 | 39031010 | 113400 | Tom Davis | On Hold | 2006-06-08 | 2009-12-11 | 2010-07-16 | 2011-05-23 | 2014-06-01
G 05-055 | DOC | WCCW - Health Care | 06-309 | 11864719 | 22130 | Dwight Hollar |  | 2006-05-24 | 2006-08-01 | 2006-11-13 | 2007-03-13 | 2010-01-01 | [5 empty] | 1
G 05-056 | DOC | WCC - Health Care Facility Remodel | 06-305 |  |  | Diana Cannon | On Hold | 2006-06-07 | 2006-06-12 | 2006-09-19 | 2006-11-15 | 2007-05-01
G 05-058 | DOC | AHCC - Minimum Security Beds (200) | 06-311 | 868000 | 116000 | Anna Crickmer |  | LEED Silver |  |  |  | 2008-09-01
G 05-059 | DOC | AHCC - New Visitation Building | 06-311 | 1975000 | 6100 | Anna Crickmer |  |  | 2006-06-12 | 2007-01-15 | 2007-05-20 | 2008-09-01 | Oct-09 |  |  |  |  | 1
| DOC | AHCC - Treatment Program Building | 08-300 | 3100000 | 9510 | Anna Crickmer |  | LEED Silver |  |  |  | 2009-06-15 | 2010-07-01
| DOC | MCCCW - 120 Bed | 06-312 | 2939189 | 12800 | Ed Hampton | 2007-07-13
G 05-060 | DOC | MCCCW - 100 Bed Housing Unit | 08-303 | 4033163 | 12800 | Ed Hampton |  | 2007-10-16 | 2007-11-26 | 2008-01-21 | 2008-06-23 | 2009-10-15 | [5 empty] | 1
| DOC | WCC - Expand Reception Center | 08-314 | 46265000 | 87583 | Diana Cannon |  | 2009-08-15 | 2010-02-15 | 2010-09-15 | 2011-07-01 | 2013-07-15 |  |  |  | 1
G 05-003 | DOC | WSP - 300 Bed Minimum Expansion | 06-327 | 47169000 | 105536 | Nanette Graham | On Hold | 2008-07-01 | 11/12009 | 2009-10-30 | 2015-07-15 | 2016-09-01 |  |  |  | 1
G 08-031 | DOC | Statewide - 300 Bed Minimum Expansion | 06-327 | 38660000 | 90229 | Nanette Graham |  | 2008-06-30 | 2012-12-30 | 2013-02-28 | 2013-04-30 | 2014-09-30 |  |  |  | 1
G 08-030 | DOC | WSP - MI Kitchen | 06-307 | 37487140 | 65089 | Nanette Graham | Dropped | 2008-06-30 | 2009-11-30 | 2010-03-01 | 2010-05-30 | 2013-04-30
| DSHS | McNeil Is. - Special Commitment Center | 06-465 | 3961603 | 53000 | Rich Christian | Dropped | 2007-10-16 | 2007-11-26 | 2008-01-21 | 2008-06-23 | 2009-07-06 | [5 empty] | 1
| DSHS | Echo Glen - Residential Housing Units Renovations | 00-405 | 10720000 | 18320 | Diana Peeples |  | LEED Silver |  |  |  | 2010-04-20 |  | 2012-02-12 |  |  |  | 1
| DSHS | Echo Glen - Residential Housing Units Renovations Ph 3 | 10-456 | 6500000 | 28120 | Diana Peeples |  | 2010-06-23 | 2010-09-07 | 2010-12-07 | 2011-06-01 | 2012-11-30
| DSHS | Green Hill School-Residential Mental Health Unit | 10-457 | 4200000 | 10500 | Diana Peeples |  | 2010-12-20 | 2011-05-04 | 2011-06-23 | 2011-09-09 | 2012-10-30
| DSHS | Green Hill School - HCA Building | 06-481 | 4300000 | 20275 | Diana Peeples |  | LEED Silver |  |  |  | 2009-10-26 |  | 2011-07-22 |  |  |  | 1
| DSHS | Green Hill School - IMU Building | 06-481 | 4200000 | 12000 | Diana Peeples | 2008-08-26
| DSHS | WSH - New Kitchen & Commissary | 08-409 | 4400000 | 50000 | Rich Christian | Dropped | [8 empty] | 1
| DOT | Alaska Way Viaduct Tunnel Operations Building | [9 empty] | 2015-06-01 |  |  |  | 1
| DOT | SR 520 Bridge Mantenance Facilities | [9 empty] | 2013-07-01 |  |  |  | 1
| DOT | Eagle Harbor Maintenance Facilities |  |  |  |  | 2007-07-30 |  |  |  |  | 2011-05-01
| DOT | Anacortes Ferry Terminal | [9 empty] | TBD |  |  |  | 1
| DOT | Mukilteo Ferry Terminal | [9 empty] | TBD |  |  |  | 1
| DOT | Seattle Ferry Terminal | [9 empty] | TBD |  |  |  | 1
| DOT | Bainbridge Island Ferry Terminal |  |  |  |  | On Hold |  |  |  |  | TBD
| DOT | Olympic Regional HQ |  |  |  |  | On Hold |  |  |  |  | TBD
G 08-011 | UW | Business School, Phase 2 (Balmer Hall) |  | 46800000 | 60878 | Brian Berard |  | 2008-03-24 | 2008-11-14 | 2009-09-01 | 2010-07-30 | 2012-10-19 |  |  |  | 1
G 05-064 | UW | Playhouse Theater Renovation | 200912 | 5660000 | 13554 | Randy Everett |  | LEED Gold |  |  |  | 2008-07-01
G 05-069 | UW | Clark Hall Renovation | 200910 | 9000000 | 30541 | Steve Tatge |  | LEED Gold |  |  |  | 2008-12-01
G 05-065 | UW | Savery Hall Renovation |  | 36200000 | 102105 | Brian Berard |  | LEED Gold |  |  |  | 2009-06-01 |  | 2010-10-05 |  |  |  | 1
G 05-067 | UW | UWT - William W. Philip Hall |  | 9400000 | 20000 | Catherine Vogt |  | LEED Gold |  |  |  | 2008-08-01 |  | 2010-11-17 |  |  |  | 1
G 08-003 | UW | Denny Hall Renovation |  | 56915000 | 87549 | Randy Everett |  | 2008-04-01 |  |  | 2008-12-01 | 2011-07-01 |  |  |  |  | 1
| UW | Ethnic Cultural Center | [9 empty] | 2012-03-01 |  |  |  | 1
| UW | Burke Museum | [9 empty] | 2015-01-01 |  |  |  | 1
| UW | Intellectual House | [13 empty] | 1
| UW | Anderson Hall | [13 empty] | 1
G 08-004 | UW | Lewis Hall Renovation |  | 25130000 | 33736 | Ken Kubota |  | 2008-04-01 | 2008-08-01 | 2008-12-01 | 2009-09-01 | 2010-12-01 |  |  |  |  | 1
G 08-010 | UW | Molecular Engineering Interdisciplinary Academic Bldg. |  | 62500000 | 52000 | Steve Tatge |  | 2008-04-01 | 2008-04-01 | 2008-09-01 | 2008-12-01 | 2011-10-01 |  |  |  |  | 1
G 08-027 | UW | Bothell Campus - Phase 3 - New Academic Building | [9 empty] | 2012-11-30 |  |  |  | 1
G 08-028 | UW | Tacoma Campus - Phase 3 - Joy Building Remodel | [5 empty] | LEED Platinum |  |  |  | 2011-01-31 |  | 2012-01-27 |  |  | 1
G 08-029 | UW | Tacoma Campus - Tioga Library (formerly Jefferson Bldg.) | [5 empty] | 2004-10-04 | 2004-10-08 | 2008-05-01 | 2009-04-07 | 2012-02-22 |  |  |  | 1
G 05-078 | WSU | Undergraduate Classroom Building - Vancouver |  |  | 58000 |  |  | LEED Silver
G 08-031 | WSU | Olympia Avenue Student Housing Project | [5 empty] | LEED Silver
| WSU | Engineering and Computer Science Building - Vancouver |  |  | 56000
| WSU | Global Animal Health |  |  | 62000
G 08-015 | WWU | Academic Instruction Center | [9 empty] | 2009-08-31 | [5 empty] | 1
G 08-016 | WWU | Buchanan Tower Addition | [9 empty] | 2010-09-01 |  |  |  |  | 1
G 08-017 | WWU | Miller Hall Renovation | PW465 | 35801240 | 133117 | David Willett |  | 2008-02-11 | 2008-02-11 | 2009-04-23 | 2009-10-06 | 2011-10-31 |  |  |  |  | 1
G 05-070 | EWU | Hargreaves Hall Renovation | AE0511 | 9292000 | 45172 | Jim Moeller |  | LEED Gold |  |  |  | 2009-02-27
G 05-071 | EWU | Patterson Hall Renovation | AE0614 | 41266000 | 139900 | Jim Moeller |  | 2008-06-02 | 2008-06-02 | 2009-04-06 | 2010-01-04 | 2013-04-29 |  |  |  | 1
G 05-073 | EWU | Student Recreation Center |  |  |  | Troy Bester |  | LEED Gold |  |  |  | 2008 |  | 1905-06-30
G 05-072 | EWU | Martin/Williamson Hall Remodel |  |  |  | Troy Bester |  | 2011 |  |  |  | 2013
G 08-018 | EWU | University Science Center |  |  |  | Troy Bester | [9 empty] | 1
G 08-014 | CWU | IET/Hogue Technology Project |  |  | 49280 | [11 empty] | 1
G 05-002 | CWU | Dean Hall Renovation | 5229 | 18038328 | 79553 | Joanne Hillemann |  | 2006-04-04 | 2006-04-04 | 2007-03-21 | 2007-09-14 | 2008-05-10 | [5 empty] | 1
G 08-032 | TESC | College Activities Bldg Add. & Renovations | 07-05 | 14000000 | 100500 | Dick Clintworth |  | LEED Gold |  |  |  | 2010-06-01 |  | 2012-03-15 |  |  |  | 1
| TESC | Lab 1 - 2nd Floor Renovation |  | 4950000 |  | Dave Shellman |  | 2011-10-01 | 2012-01-15 | 2012-03-15 | 2012-05-15 | 2013-06-30
G 05-074 | TESC | Daniel J Evans Library Modernization - Phase 2 | F06007 | 14323000 | 87000 | Hal Van Gilder |  | 2007-03-16 | 2006-09-10 | 2007-03-07 | 2008-01-28 | 2008-11-01 | [5 empty] | 1
|  |  | Totals | 1645017525 | 5122690 | [6 empty] | No. of LEED Projects that are Certified: |  | 0 |  | 27 | 27 | 23
|  | Key |  |  | Points |  |  |  |  | In Desgin = | 27
|  | LEED Platinum |  |  | 52+
|  | LEED Gold |  |  | 39-51 |  |  |  |  | In Construction = | 27
|  | LEED Silver |  |  | 33-38
|  | LEED Certified |  |  | 26-32 |  |  |  |  | Occupied, but not yet LEED Certified = | 23
Projects Dropped or On-Hold
This project will not seek LEED certification or follow DES QA process
Bala