## Sheet1
This 90-day sample timeline identifies typical components included in a recruitment plan and helps to keep the activities on track. It can be used to tailor any type of recruitment whether it be a classified service, professional or a management position. It is a tool that visually describes the steps involved in a recruitment effort. The tool works well when working with your hiring manager to describe each step and who is responsible; it gets their commitment to the process as well as identifies their tasks.
| Projected |  | Notes | Who | Actual
Activity | Begin | Through |  |  | Begin | Through
Initial Consultation | Day 1 |  |  | HR & Hiring Manager
Position Description Development | Day 3 | Day 10 |  | HR & Hiring Manager
Marketing/Ad Campaign Development | Day 3 | Day 10 |  | HR
Marketing/Outreach/Networking Campaign | Day 10 | Day 40 |  | HR
Applicant Screening | Day 10 | Day 50 | Determines Viabilility | HR
Candidate Assessment | Day 40 | Interviews | Formal | HR
Interview Question Development | Day 10 | Pre-Interview |  | HR & Hiring Manager
Pre-interview Client Consultation | Day 50 |  | Candidate Review | HR & Hiring Manager
Interview Question Selection | Pre-Interview |  |  | HR & Hiring Manager
Schedule/Coordinate Interviews | Day 51 |  |  | HR
First Round Interviews | Day 61 |  |  | HR & Hiring Manager
Background/Reference Checks on Finalists | Day 62 | Day 72 | Requires 10 days | HR
Submit Finalists for Review | Day 73 |  |  | HR
Final Interviews | Day 74 |  |  | HR & Hiring Manager
Offer Position | Day 75 |  | Allows for notice | Hiring Manager
Send Regrets to Remaining Applicants | Day 76 |  |  | HR
New Employee Starts | Day 90 |  |  | Candidate